| SWICIC BusinessLINC Schedule: 2002 |
| --- |
| Milestone and performance goal achievements to be reported monthly and in Quarterly Performance Reports. Project Phase/Milestone Starting Ending Submit 1st Quarter Reports 01/15/02 Large Business Outreach Plan 01/17/02 Ongoing Develop SWICIC Web Site-Informational 01/21/02 02/06/02 Small Business Outreach Plan 02/07/02 Ongoing On-Line Database Development 02/11/02 03/01/02 Enable Web Site-Database Access 03/15/02 Enable Business Registration on Web 03/22/02 Execute Business Matching Services Assistance Plan 03/11/02 09/30/02 Submit 2nd Quarter Reports 04/15/02 Achieve 25 Small Business ½ Goal 05/10/02 Achieve 15 Linkages ½ Goal 05/23/02 Achieve 15 Large Business Goal 06/14/02 Achieve 50 Small Business Goal 07/05/02 Submit 3rd Quarter Reports 07/15/02 Achieve 60 Jobs ½ Goal 07/25/02 Achieve 30 Linkages, 120 Jobs, and $15 Million New Contract Goals 09/30/02 Contract End Yr-1 Prepare & Submit 4th Quarter/Final Reports 11/01/02 11/15/02 | 2002 January 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 31 February 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 March 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 31 April 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 May 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 31 June 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 July 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 31 August 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 31 September 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 October 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 31 November 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 December 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30 31 |